Annex V.

# Work Plan of the Carpathian Wetland Initiative for period 2009-2011

| Activity | Relations to the draft Ramsar Strategic Plan | 2009 | 2010 | 2011 | Budget (EUR) |
| --- | --- | --- | --- | --- | --- |
| I. Platform of basic data on wetlands |
| 1.1. Organising of the first 3 days Carpathian wetland conference with participation of relevant experts, national authorities, international partners and NGOs from all Carpathian countries. | Strategy 1.1 Wetland inventory and assessment; 1.4 Cross-sectoral recognition of wetland services; 3.4 Sharing information and expertise; 4.1 CEPA |  |  |  | 25,000 |
| 1.2. Development of harmonised classification system of wetland habitats used in EU, compatible protocol for wetland inventory, guidelines for evaluation and interpretation of data for all Carpathian countries using experience and work of the BBI-MATRA/DBU/CERI projects and Natura 2000/Emerald network development. | Strategy 1.1 Wetland inventory and assessment; 1.2 Global wetland information; 1.7 Invasive species; 2.2 Ramsar site information; 3.4 Sharing information and expertise; 3.5 Shared wetlands, basins and species |  |  |  | 25,000 |
| 1.3. Training and workshop on field manual use, field mapping, storing of data, digitising. | Strategy 1.1 Wetland inventory and assessment; 3.4 Sharing information and expertise; 4.1 CEPA |  |  |  | 3,000 |
| 1.4. Collection and harmonisation of data for Overview of Carpathian Wetlands – inventory in all countries, GIS polygons, identification of wetlands of international importance and of sites in need of restoration, as well as transboundary wetland sites in cooperation with neighbour institutions. | Strategy 1.1 Wetland inventory and assessment; 1.2 Global wetland information; 1.6 Wetland restoration; 1.7 Invasive species; 2.1 Ramsar site designation; 2.2 Ramsar site information; 2.4 Ramsar site ecological character; 2.6 Ramsar site status; 3.4 Sharing information and expertise; 3.5 Shared wetlands, basins and species |  |  |  | 20,000 |
| 1.5. Involvement in the 2012 PA4LP Carpathian Clearing House Mechanism. | Strategy 1.2 Global wetland information; 3.1 Synergies with MEAs; 3.4 Sharing information and expertise |  |  |  | 2,000 |
| II. Platform for cooperation |
| 2.1. Organizing of meetings and electronic communication of members of the CWI Board, using preferably other relevant events and support of travel expenses if necessary. | Strategy 1.3 Policy, legislation and institutions; 3.2 Regional initiatives; 3.3 International assistance; 4.3 Convention bodies’ effectiveness |  |  |  | 15,000 |
| 2.2. Facilitation of effective cooperation between the environmental, water management and other relevant sectors in respective Carpathian countries, coordination of national teams, expert networks and institutions. | Strategy 1.3 Policy, legislation and institutions; 1.4 Cross-sectoral recognition of wetland services; 1.5 Integrated Water Resources Management; 1.8 Private sector; 1.9 Incentive measures; 4.3 Convention bodies’ effectiveness |  |  |  | 15,000 |
| 2.3. Regular reporting to the Secretariats of the Carpathian and Ramsar Conventions and to the CWI Board. | Strategy 3.1 Synergies with MEAs and IGOs; 3.2 Regional initiatives; 4.3 Convention bodies’ effectiveness |  |  |  | 1,500 |
| III. platform for wetland assessment and monitoring |
| IV. PLATFORM FOR INTEGRATED RIVER BASIN MANAGEMENT ESPECIALLY IN SHARED CATCHMENTS |
| 4.1. Involvement in the preparation of the protocol or other relevant documents on sustainable and integrated water/river basin management within the Carpathian Convention in cooperation with other partners, and involvement in relevant projects (especially ICPDR/UNDP/ GEF project in the Tisa/Tisza River basin) | Strategy 1.3 policy, legislation and institutions; 1.4 Cross-sectoral recognition of wetland services; 1.5 Integrated Water Resources Management; 1.9 Incentive measures; 2.5 Ramsar site management effectiveness; 3.1 Synergies with MEAs and IGOs; 3.4 Sharing information and expertise |  |  |  | 3,000 |
| 4.2. Organising of national seminars/workshops for relevant national authorities at river basin level on wetland management and water allocation to wetlands within the river basin management plans using Ramsar guidance (Handbook 7 “River Basin Management”) and the EU Water Framework Directive Guidance Document 12 (“The Role of Wetlands in the Water Framework Directive”). | Strategy 1.3 Policy, legislation and institutions; 1.4 Cross-sectoral recognition of wetland services; 1.5 Integrated Water Resources Management; 2.3 Management planning; 3.4 Sharing information and expertise; 3.5 Shared wetlands, basins and species; 4.1 CEPA |  |  |  | 14,000 |
| 4.3. Facilitation of bilateral consultations and meetings on integrating wetlands into river basin management in shared wetlands and catchments, bilateral agreements on recognizing common objectives and principles of their management and wise use, based on experience of successful case studies. | Strategy 1.3 Policy, legislation and institutions; 1.4 Cross-sectoral recognition of wetland services; 1.5 Integrated Water Resources Management; 2.3 Management planning; 3.4 Sharing information and expertise; 3.5 Shared wetlands, basins and species |  |  |  | 6,000 |
| 4.4. Develop/prepare handbooks and/or brochures, leaflets on special aspects. | Strategy 4.1 CEPA |  |  |  | 20,000 |
| V. Platform for wetland restoration activities |
| 5.1. Develop wetland restoration strategies/policies for montane/submontane wetlands in a number of Carpathian countries. | Strategy 1.3 Policy, legislation and institutions; 1.6 Wetland restoration |  |  |  | 4,000 |
| 5.2. Identify priority sites and pilot sites for restoration from results of national wetland inventories especially in the Tisa/Tisza River basin (demonstration projects). | Strategy 1.1 Wetland inventory and assessment; 1.6 Wetland restoration |  |  |  | 2,000 |
| VI. PLATFORM FOR Capacity building and public awareness |
| 6.1. Preparation, distribution and evaluation of a questionnaire on training priorities and needs and development of training modules and training programme according to results of the questionnaire. | Strategy 4.1 CEPA |  |  |  | 1,000 |
| 6.2. Organisation of training courses for trainees from the Carpathian countries focused on priorities. | Strategy 4.1 CEPA |  |  |  | 8,000 |
| 6.3. Establish web page of CWI and publish information on wetlands and their role and function in the landscape and for human wellbeing in the Carpathians. | Strategy 1.2 Global wetland information; 1.4 Cross-sectoral recognition of wetland services; 3.4 Sharing information and expertise; 4.1 CEPA |  |  |  | 3,000 |
| 6.4. Establishment of a database of educational and training institutions and experts aimed at wetlands and communication with them. | Strategy 1.2 Global wetland information; 3.4 Sharing information and expertise; 4.1 CEPA |  |  |  | 1,500 |
| 6.5. Development and production of brochures, leaflets and posters on the Carpathian wetlands and their functions and services for human wellbeing and for biodiversity to support campaigns, and their presentation on web page. | Strategy 1.4 Cross-sectoral recognition of wetland services; 4.1 CEPA |  |  |  | 12,000 |
| 6.6. Establishment and support for regional Wetland Centre and its activities (coordination, information transfer, education, information sources collection, fund raising, harmonisation with the CC Protocol on Biodiversity, Working Group on Biodiversity of the Carpathian Implementation Committee, WWF project 2012 Protected Areas for Living Planet and the Clearing House Mechanism, Carpathian Network of Protected Areas, CERI etc.), based on the lessons learnt from the study tour focused on Wetland Centres in Europe. | Strategy 1.3 Policy, legislation and institutions; 3.1 Synergies with MEAs and IGOs; 3.2 Regional initiatives; 3.3 International assistance; 3.4 Sharing information and expertise; 4.1 CEPA; 4.3 Convention bodies’ effectiveness |  |  |  | 40,000 |